MINUTES OF THE MEETING ON THE PLANNING AND SCHEDULING OF THE WASTE AND MANAGEMENT SEMINAR AND ORIENTATION FOR ALL DEPARTMENTS AND SECTIONS OF THE CAMPUS, NOVEMBER 17, 2025

I. CALL TO ORDER

The meeting was formally called to order at 5:12 in the afternoon by Hon. Kathlyn L. Baclayon, President of the Supreme Student Government (SSG).

In attendance were the House Representatives and Senators of the SSG Office, the members of the Equationers Organization, and Engr. Mary Ellen C. Camarillo, Chairperson of the Bachelor of Science in Industrial Engineering (BSIE) Program. The meeting was convened to comprehensively discuss and plan the Waste Management Seminar and Community Extension Project to be implemented campus-wide.

II. STATEMENT OF PURPOSE

A. Project Overview

Engr. Mary Ellen C. Camarillo provided an extensive overview of the project, emphasizing that it aims to educate and mobilize the entire university community in the practice of proper waste segregation, collection, and disposal. She elaborated that Taiheiyo Cement Philippines, Inc. has entered into a cooperative engagement with the university, wherein collected single-use plastics and residual wastes may serve as alternative fuel or raw materials in their industrial processes. This aligns with the company’s sustainability objectives and directly supports the university’s environmental mission.

Engr. Camarillo clarified that this project, while typically associated with the College of Agriculture, Forestry, and Environment (CAFÉ), is officially an extension initiative of the BSIE Department, approved in consultation with Dr. Steve Michael Alcazar, Chairperson of CAFÉ. Dr. Alcazar, however, recommended that all activities be coordinated with the SSG Office to ensure unified student participation and compliance across all departments.

B. Purpose and Scope of the Orientation

The principal focus of the meeting was the planning of a structured and synchronized series of seminars and orientations to disseminate the guidelines and rationale behind the waste management initiative.

The meeting body collectively agreed that the orientation shall be executed through a top-down information flow of communication, ensuring comprehensive and effective information dissemination:

- The SSG House Representatives, Senators, and members of the Equationers Organization shall spearhead the orientation sessions in collaboration with Departmental Organization Presidents.

- The sessions will be conducted per college and department, targeting section mayors and year-level officers as primary attendees.

- The section mayors, in turn, shall relay and reinforce the information to their respective blockmates and classmates, under the supervision of the departmental organization presidents.

This systematic approach ensures that every student in the university will be properly informed of their role and accountability in implementing the waste management system.

C. Implementation Guidelines

Engr. Camarillo reiterated that proper waste segregation shall be strictly enforced throughout the campus. A total of 111 labeled trash bins, classified into biodegradable, non-biodegradable, and recyclable, have been strategically installed across various departments and building complexes.

Each bin carries visible instructional labels and reminders on the proper disposal of waste materials. Failure to comply with segregation guidelines shall warrant the imposition of penalties, while consistent observance of the proper disposal system shall merit incentives and recognition during the Annual Founding Anniversary, as endorsed to the Student Affairs and Services (SAS) Office.

D. Funding and Resource Management

Engr. Camarillo disclosed that the procurement of the trash bins was made possible through a temporary financial assistance extended by Sir Malaki. The Equationers Organization initially shouldered the expenses for garbage bags used during the pilot implementation.

Due to the unsustainable cost of continuous garbage bag procurement, Engr. Camarillo proposed the use of reusable sacks as a more economical and environmentally sustainable alternative.

She also raised the necessity of establishing a Material Recovery Facility (MRF) within campus premises to properly sort and store collected wastes, noting that budget inquiries and site assessments will be made in coordination with Dr. Steve Michael Alcazar. Moreover, the establishment of a composting facility for biodegradable wastes was also proposed to further support sustainable waste processing within the university.

E. Monitoring and Evaluation

The Equationers Organization, through its President Hon. Daugdaug and Vice President Hon. Cantil, formulated a checklist-based monitoring system to evaluate the cleanliness and compliance level of each department.

Their initial inspections, while visiting the premises of the CHMT, revealed instances of improper segregation, thereby reinforcing the urgency of conducting orientation seminars to educate and correct waste disposal practices before the full rollout of the initiative.

F. Incentive and Penalty Framework

Hon. Kathlyn L. Baclayon suggested benchmarking the penalty implementation on the existing Environmental Code of the University, which prescribes disciplinary measures for environmental violations. However, since the said code remains pending for official approval, a resolution will be prepared to formally authorize its temporary adoption in support of this project.

Penalties may include monetary fines, the proceeds of which shall be allocated to future environmental programs and clean-up initiatives. Departments exhibiting exemplary compliance shall receive commendations and non-monetary rewards through the SAS Office.

G. Scheduling and Operational Planning

After thorough deliberation, it was agreed that the initial series of orientations will be conducted on Wednesday after class hours, involving the following colleges:

- College of Arts and Sciences (CAS)

- College of Education (COED)

- College of Agriculture, Forestry, and Environment (CAFÉ)

- College of Technology and Engineering (COTE)

- College of Hospitality Management and Tourism (CHMT)

Each orientation session will last approximately twenty (20) to thirty (30) minutes, conducted simultaneously across designated venues.

Every officiating team shall be composed of:

- House Representatives and Senators of the SSG Office,

- Three (3) members of the Equationers Organization, and

- Respective Departmental Organization Presidents.

Engr. Mary Ellen C. Camarillo shall issue the official memorandum and the list of designated facilitators for each session. The House Representatives and Equationers are tasked to submit the list of departmental mayors prior to the scheduled date, more specifically, tonight, November 17, 2025.

Furthermore, Hon. Daugdaug volunteered to prepare a standardized PowerPoint presentation, ensuring uniformity of content and messaging throughout all orientations.

H. Community Extension Integration

Engr. Camarillo also shared that the project has been successfully extended beyond the university campus, particularly in Barangay Tulic, where the initiative operates on an incentive-based approach: residents receive one (1) kilogram of rice for every kilogram of single-use plastics collected. This initiative exemplifies the project’s potential to foster environmental responsibility and community engagement beyond institutional boundaries.

V. ADJOURNMENT

There being no further matters to discuss, Hon. Kathlyn L. Baclayon formally adjourned the meeting at 5:56 PM.

____________________________________________________________________________

I hereby certify to the correctness of the foregoing minutes concerning the planning and scheduling of the waste and management orientation and seminar

Prepared by:

JANQUEL B. GEAGONIA

Executive Secretary, SSG

Attested by:

KATHLYN L.BACLAYON

President, SSG